## Project Timeline
Column1 | Column2 | Column3 | Column4
Day | Date | Tasks | Deliverables
Day 1 | 13 Oct | Project kickoff, define objectives, repo setup | Proposal + GitHub repo
Day 2 | 14 Oct | Dataset cleaning & preprocessing | Clean dataset + preprocessing script
Day 3 | 15 Oct | EDA (graphs, distributions, insights) | EDA notebook/report
Day 4 | 16 Oct | Implement Model 1 (TF‑IDF + Logistic Regression) | Trained baseline model
Day 5 | 17 Oct | Train Transformer Model (DistilBERT) | Transformer model saved
Day 6 | 18 Oct | Evaluation + comparison + tuning | Comparison table + best model
Day 7 | 19 Oct | Integration pipeline + unified inference | Integrated model pipeline
Day 8 | 20 Oct | Build Streamlit UI layout | Local Streamlit app
Day 9 | 21 Oct | Connect models to Streamlit UI, prediction logic | Interactive app working locally
Day 10 | 22 Oct | Deployment prep: requirements, config | Ready-to-deploy folder
Day 11 | 23 Oct | Deploy on Streamlit Cloud | Live app link
REST BREAK | 3–7 Nov | University Mid Exams | —
Day 12 | 8 Nov | Enhance UI + add PHQ‑9 module | PHQ‑9 scoring integrated
Day 13 | 9 Nov | Improve explanations + add risk scoring | Explanation outputs in app
Day 14 | 10 Nov | Final documentation writing | Full tech report
Day 15 | 11 Nov | Testing + repo cleanup | Cleaned GitHub repo
Day 16 | 12 Nov | CI/CD auto-redeploy setup | Auto-build on commit
Day 17 | 13 Nov | Final revisions, screenshot capture | Finalized report assets
Day 18 | 14 Nov | Create PDF + Medium Article + Slides prep | Final PDF, Medium Article
Day 19 | 15 Nov | Project submission day | Submission package